## Project Details
Project Name | Smart Procurement Vendor Management System
Duration | 8 Weeks
Methodology | Agile Scrum

## Product Backlog
Epic | User Story ID | User Story | Priority | Story Points | Sprint
Vendor Management | US1 | Register vendor | High | 5 | Sprint 1
Vendor Management | US2 | Create dashborad-Admin,Employee,Manager,Vendor,Finance | High | 3 | Sprint 1
Procurement | US3 | Create requisition | High | 5 | Sprint 2
Procurement | US4 | Approve requisition | High | 8 | Sprint 2
PO Tracking | US5 | Track purchase order | Medium | 5 | Sprint 3
Reports | US6 | Generate cost report | Medium | 8 | Sprint 3
Security | US7 | Role-based login | High | 5 | Sprint 4

## Sprint Plan
Sprint | Goal | Start | End
Sprint 1 | Setup + Vendor Module+Dashboards | Week 1 | Week 2
Sprint 2 | Procurement Workflow | Week 3 | Week 4
Sprint 3 | PO Tracking + Reports | Week 5 | Week 6
Sprint 4 | Security | Week 7 | Week 8

## Task Tracking
Task | Assigned To | Status | Comments
Vendor Registration API | Dev1 | Completed
Approval Workflow API | Dev2 | Completed
PO Tracking Module | Dev3 | Completed
Report Generation | Dev4 | Completed